## sample processing log
Site | plot | year | sample started | sample finished

## grazer processing progress
sample year | site | Priority | number of plots available | number finished | prelim graph sent to Mary | deadline | notes
2016 | Csan | 1 | 9
2016 | Clow | 1 | 9
2016 | TqS | 1 | 9
2016 | TqN | 1 | 9
2016 | MmN | 2 | 9
2016 | MmS | 2 | 9
2016 | GSe | 2 | 9
2016 | GSw | 2 | 9
2016 | Pth | 3 | 9
2016 | Ptp | 3 | 9
2017 | Csan | 1 | 9
2017 | Cinner | 1 | 9
2017 | TqN | 1 | 9
2017 | TqS | 1 | 9
2017 | PbS | 2 | 9
2017 | PbN | 2 | 9
Sample processing: Proceed through all the sites and years, doing 6 plots per site. This will allow us to start making graphs and comparisons. Then, go back and do the remaining 3 per site (if needed after analysis). When you finish 6 plots from a site, please send Mary the data and a figure from the site - any figure is fine, but something you're interested in! Communicate regularly about progress, if it's faster or slower. We do need all these done by March or so, so we can plan field work for next summer.

## overall hakai project planning
Project | data | year of data | Lead | goal | date | goal achieved
Smithora transplant |  | 2015 | Gwen | do the experiment | 2015 | yes
|  | 2015 | Ang | smithora surveys | 2015 | yes
|  |  |  | draft ms | 2017
Microbial transplant